IT Project Manager

APPRENTICESHIP APPROACH

Competency

O*NET-SOC CODE

11-3021.00

RAPIDS CODE

1048

| Work Process Schedule | SKILLS |  |
| --- | --- | --- |
| PROJECT STRATEGY & LIFE CYCLE Generate and refine a preliminary project concept definition Determine the business need and feasibility of the project Identify project sponsors who will help obtain resources Create a written business case Create a first cut project charter Identify an appropriate project life cycle (phases, tracks of work &amp; deliverables) Estimate phase transition dates Summarize the project life cycle in a PowerPoint/Visio drawing Perform Post-it note exercise Create a release strategy Obtain formal approval from the project sponsor Confirm management authorization to begin planning Capture issues in an issue log Perform Initiate/Concept phase exit quality gate review | 14 | 300 |
| DEFINED ROLES AND ORGANIZATION Given a project charter, recruit project team members Create a project team organization using matrix (strong or weak) concepts Develop and deliver a presentation describing roles/responsibilities of the project manager, sponsor, skill center managers, project leaders, team members and stakeholders Identify project stakeholders Identify project sponsor Verify that sponsor understands his/her role in the process Identify and document organizational and process issues Close all issues for the phase regarding org structure, roles and process | 8 | 300 |
| STABLE SCOPE AND REQUIREMENTS Given an approved business case create a high level Statement of Work (SOW) or project charter Identify Product Scope document by using: 1) a simple requirements document or 2) QFD breakdown listing performance requirements at primary, secondary and tertiary levels as required Document product specifications (i.e., objective measures of requirements) as required per QFD approach Map product requirements to stakeholder objectives and identify gaps Identify issues and gaps related to functionality (i.e., requires that can be delivered versus requirements requested) Identify Project Scope by creating work breakdown structure (WBS.) Drill down WBS to the activity level Verify that WBS contains all project phases and tracks of work Review project scope with appropriate stakeholders Identify all open scope and requirements issues Close all scope and requirements issues for the phase Per QFD approach, develop a strategy to ensure that requirements are mapped, checked and managed in each of the implementation phases prior to phase exit | 12 | 800 |
| CHANGE CONTROL Select the appropriate change order form/tool Develop a presentation describing the change order process Explain the change order process to all team members and stakeholders Formalize requested changes of scope and requirements by using the change order process | 4 | 100 |
| PLANNED COMMITMENTS Project WBS activities entered into appropriate scheduling tool All activities assigned accountable 'owners' All activities estimated for most likely durations or for highly uncertain activities, durations are estimated using three point approach Effort driven activities are estimated by hours/days and prioritized. Required resources are estimated Logic ties are assigned linking all activities creating a network to enable calculation of total float The project schedule is calculated through all phases and tracks of work The project critical path is identified Resources are assigned and the project is rescheduled based upon resource constraints Phase transition milestones are highlighted Project contingency time is added as required The project schedule is reviewed against stakeholder requirements The project schedule is reviewed against product requirements The team feels ownership of the schedule Schedule issues are closed during the planning phase(s) Baseline dates are set The project schedule is published and communicated to stakeholders The change control/change order process is applied to the project schedule following the planning phase(s) Rolling wave planning (i.e., progressive detailing) is performed during the execution phases as required | 18 | 800 |
| PERFORMANCE MEASUREMENT Project team meetings occur regularly. Performance metrics are presented at those meetings and performance shortfalls are flagged Project metrics are used in project reviews with the project sponsor and senior stakeholders Tracking of the schedule adherence is performed routinely. Variances are flagged Baseline and actual start/finish dates and percent complete are recorded on a scheduling tool The project schedule is recalculated each week highlighting projected variances versus plan and total float Activity completion S-Curves (actual versus plan) are used and updated on a weekly basis Budget S-curves (actual versus plan) are updated on at least a monthly basis The Estimate at Complete (EAC) forecast is compared with Budget at Complete (BAC) to identify cost variances Appropriate reporting metrics using graphical tools are created and maintained for key deliverables such as configurations, data records, testing, reports, forms etc. Resource gap reports/metrics are produced highlighting resource shortfalls Project performance metrics are posted openly and publicly to all stakeholders Forecasts are produced for scope, schedule and budget at regular intervals The issue log is updated routinely Project metrics are used effectively to trigger escalation and corrective action Risk removal and mitigation plans are tracked routinely Project Manager keeps the customer well informed Quality metrics are utilized | 18 | 800 |
| PHASE REVIEWS, QUALITY MANAGEMENT & QUALITY GATES Phase exit review milestones are integrated into the project plan Phase exit criteria are identified, measured for sufficiency and openly reported Phase exit reviews (i.e. quality gate reviews) occur and areas of insufficiency are rigorously identified as open issues Phases are reported as complete only when sufficiency is actually achieved Sufficient quality processes are built into the development of project deliverables. Key product deliverables produced within each phase are mapped to the original requirements of the project and/or the Statement of Work (SOW) and the business case. Gaps are identified and formally managed as issues throughout the project life cycle Appropriate testing practices are part of the project life cycle (methodology) | 8 | 600 |
| ISSUE MANAGEMENT AND CORRECTIVE ACTION An issue log is used to record and review issues Issues are reviewed regularly at team meetings Issues are followed up and discharged in a timely manner Tough issues are not hidden but openly and aggressively confronted The project manager follows up with team members who own deliverables that are falling behind plan in a timely manner The project manager rigorously works with team members who are operating behind plan to develop and implement recovery strategies Issues are escalated as required The project manager keeps the customer and project sponsor well informed | 8 | 1K |
| PROJECT LEADERSHIP AND COMMUNICATIONS Provides adequate direction and work instructions to team members Inspires and motivates team members Confronts tough issues (as opposed to dodging those issues) Spends time leading the team Secures decisions from team members and stakeholders Demonstrates stability and consistency in his/her direction Runs team meetings effectively Delegates and holds team members accountable Facilitates crisis resolution effectively Uses project metrics appropriately Uses good judgment Maintains the 'appropriate' level of stress on the project environment, not too much &amp; not too little Performs 'Integration' management and coordination effectively Manages project risks effectively Secures corrective action as required Ensures appropriate project communications exist | 16 | 1.2K |
| MULTI-PROJECT MANAGEMENT/SKILL CENTER MANAGEMENT Creates a prioritized list of existing projects Updates monthly/quarterly high level multi-project schedule update report Creates and documents a process for handling new project requests Creates a Resource Breakdown Structure (RBS) Inputs projects into scheduling tool by phase Loads resources into project scheduling tool (High Level only) Resolves multi-project resource issues Produces resource assignment/loading and exception reports Utilizes multi-project change control effectively Receives project status reports from project managers and updates multi-project scheduling model Organizes formal meetings for resource/project reprioritization | 11 | 100 |
| Totals | SKILLS 117 | OJT HRS 0 |